## Defects_Log
Defect ID | Sprint | Module | Severity | Priority | Status | Date Raised | Date Resolved | Days Open | SLA Breach | Tester
DEF-1000 | Sprint 1 | Payments | High | P3 | Resolved | 2024-01-10 | 2024-01-11 | 1 | No | Chris L.
DEF-1001 | Sprint 1 | Login | Medium | P1 | Resolved | 2024-01-16 | 2024-01-24 | 8 | No | Chris L.
DEF-1002 | Sprint 1 | API | High | P3 | Resolved | 2024-01-11 | 2024-01-17 | 6 | Yes | Swarleen B.
DEF-1003 | Sprint 1 | Reporting | Medium | P2 | Resolved | 2024-01-12 | 2024-01-13 | 1 | No | Jordan T.
DEF-1004 | Sprint 1 | API | High | P2 | Resolved | 2024-01-13 | 2024-01-21 | 8 | Yes | Swarleen B.
DEF-1005 | Sprint 1 | Payments | Medium | P3 | Reopened | 2024-01-14 |  | 107 | Yes | Chris L.
DEF-1006 | Sprint 1 | Reporting | High | P3 | Closed | 2024-01-13 | 2024-01-21 | 8 | Yes | Swarleen B.
DEF-1007 | Sprint 1 | Reporting | Critical | P2 | Resolved | 2024-01-09 | 2024-01-14 | 5 | Yes | Swarleen B.
DEF-1008 | Sprint 1 | User Mgmt | High | P3 | Closed | 2024-01-10 | 2024-01-14 | 4 | No | Alex M.
DEF-1009 | Sprint 1 | Dashboard | Medium | P3 | Resolved | 2024-01-09 | 2024-01-17 | 8 | No | Chris L.
DEF-1010 | Sprint 1 | Reporting | Medium | P2 | Resolved | 2024-01-18 | 2024-01-28 | 10 | No | Jordan T.
DEF-1011 | Sprint 1 | Notifications | Low | P3 | Resolved | 2024-01-08 | 2024-01-17 | 9 | No | Jordan T.
DEF-1012 | Sprint 1 | Reporting | Critical | P4 | Resolved | 2024-01-19 | 2024-01-20 | 1 | No | Priya K.
DEF-1013 | Sprint 1 | Reporting | High | P4 | Resolved | 2024-01-12 | 2024-01-13 | 1 | No | Chris L.
DEF-1014 | Sprint 1 | User Mgmt | Medium | P3 | Resolved | 2024-01-17 | 2024-01-22 | 5 | No | Alex M.
DEF-1015 | Sprint 1 | Payments | Low | P2 | Resolved | 2024-01-20 | 2024-01-21 | 1 | No | Alex M.
DEF-1016 | Sprint 1 | Notifications | Medium | P3 | Resolved | 2024-01-09 | 2024-01-14 | 5 | No | Chris L.
DEF-1017 | Sprint 1 | Login | Low | P3 | Reopened | 2024-01-21 |  | 100 | Yes | Swarleen B.
DEF-1018 | Sprint 1 | Payments | Medium | P3 | Resolved | 2024-01-18 | 2024-01-22 | 4 | No | Jordan T.
DEF-1019 | Sprint 1 | API | Medium | P3 | Reopened | 2024-01-19 |  | 102 | Yes | Chris L.
DEF-1020 | Sprint 1 | API | Medium | P3 | In Progress | 2024-01-18 |  | 103 | Yes | Chris L.
DEF-1021 | Sprint 1 | Login | Medium | P2 | Closed | 2024-01-16 | 2024-01-27 | 11 | Yes | Chris L.
DEF-1022 | Sprint 1 | Reporting | High | P1 | Closed | 2024-01-21 | 2024-01-24 | 3 | No | Swarleen B.
DEF-1023 | Sprint 1 | Search | High | P3 | In Progress | 2024-01-19 |  | 102 | Yes | Swarleen B.
DEF-1024 | Sprint 1 | Search | Low | P3 | In Progress | 2024-01-18 |  | 103 | Yes | Chris L.
DEF-1025 | Sprint 1 | Reporting | High | P3 | Resolved | 2024-01-11 | 2024-01-18 | 7 | Yes | Jordan T.
DEF-1026 | Sprint 1 | Payments | High | P3 | Resolved | 2024-01-16 | 2024-01-22 | 6 | Yes | Alex M.
DEF-1027 | Sprint 1 | Reporting | High | P2 | Resolved | 2024-01-11 | 2024-01-19 | 8 | Yes | Swarleen B.
DEF-1028 | Sprint 2 | User Mgmt | Medium | P1 | In Progress | 2024-01-22 |  | 99 | Yes | Swarleen B.
DEF-1029 | Sprint 2 | Search | Medium | P2 | Resolved | 2024-01-30 | 2024-01-31 | 1 | No | Alex M.
DEF-1030 | Sprint 2 | Notifications | Medium | P4 | Resolved | 2024-01-23 | 2024-02-01 | 9 | No | Jordan T.
DEF-1031 | Sprint 2 | Payments | Medium | P3 | Closed | 2024-02-01 | 2024-02-10 | 9 | No | Swarleen B.
DEF-1032 | Sprint 2 | Reporting | Medium | P2 | Closed | 2024-01-25 | 2024-01-27 | 2 | No | Chris L.
DEF-1033 | Sprint 2 | Payments | Medium | P3 | Resolved | 2024-01-25 | 2024-02-06 | 12 | Yes | Priya K.
DEF-1034 | Sprint 2 | Login | Low | P4 | In Progress | 2024-02-01 |  | 89 | Yes | Swarleen B.
DEF-1035 | Sprint 2 | Reporting | Low | P4 | Resolved | 2024-01-29 | 2024-02-12 | 14 | No | Priya K.
DEF-1036 | Sprint 2 | API | Low | P2 | Open | 2024-01-28 |  | 93 | Yes | Priya K.
DEF-1037 | Sprint 2 | Search | High | P3 | Closed | 2024-02-03 | 2024-02-10 | 7 | Yes | Alex M.
DEF-1038 | Sprint 2 | Login | High | P2 | In Progress | 2024-02-02 |  | 88 | Yes | Jordan T.
DEF-1039 | Sprint 2 | Dashboard | Critical | P3 | Resolved | 2024-02-04 | 2024-02-07 | 3 | Yes | Swarleen B.
DEF-1040 | Sprint 2 | Reporting | Low | P1 | Resolved | 2024-01-31 | 2024-02-01 | 1 | No | Priya K.
DEF-1041 | Sprint 2 | Payments | High | P4 | Resolved | 2024-01-31 | 2024-02-01 | 1 | No | Priya K.
DEF-1042 | Sprint 2 | User Mgmt | Medium | P3 | Resolved | 2024-01-26 | 2024-01-28 | 2 | No | Alex M.
DEF-1043 | Sprint 2 | Payments | High | P2 | Resolved | 2024-01-29 | 2024-02-02 | 4 | No | Swarleen B.
DEF-1044 | Sprint 2 | Reporting | Medium | P4 | Reopened | 2024-01-23 |  | 98 | Yes | Chris L.
DEF-1045 | Sprint 2 | API | High | P4 | Closed | 2024-01-25 | 2024-01-29 | 4 | No | Alex M.
DEF-1046 | Sprint 2 | Login | Medium | P3 | Resolved | 2024-02-03 | 2024-02-12 | 9 | No | Chris L.
DEF-1047 | Sprint 3 | Payments | Low | P2 | Closed | 2024-02-09 | 2024-02-11 | 2 | No | Chris L.
DEF-1048 | Sprint 3 | API | High | P2 | Resolved | 2024-02-10 | 2024-02-12 | 2 | No | Chris L.
DEF-1049 | Sprint 3 | Notifications | Medium | P4 | Closed | 2024-02-06 | 2024-02-15 | 9 | No | Jordan T.
DEF-1050 | Sprint 3 | Dashboard | Critical | P2 | In Progress | 2024-02-09 |  | 81 | Yes | Priya K.
DEF-1051 | Sprint 3 | Dashboard | Medium | P3 | Open | 2024-02-06 |  | 84 | Yes | Chris L.
DEF-1052 | Sprint 3 | Login | Critical | P2 | Resolved | 2024-02-11 | 2024-02-12 | 1 | No | Jordan T.
DEF-1053 | Sprint 3 | User Mgmt | High | P4 | Reopened | 2024-02-05 |  | 85 | Yes | Alex M.
DEF-1054 | Sprint 3 | Notifications | Medium | P3 | Resolved | 2024-02-13 | 2024-02-26 | 13 | Yes | Chris L.
DEF-1055 | Sprint 3 | Dashboard | Medium | P4 | Resolved | 2024-02-07 | 2024-02-18 | 11 | Yes | Priya K.
DEF-1056 | Sprint 3 | Reporting | Critical | P3 | Resolved | 2024-02-11 | 2024-02-16 | 5 | Yes | Jordan T.
DEF-1057 | Sprint 3 | Reporting | High | P3 | Resolved | 2024-02-05 | 2024-02-11 | 6 | Yes | Alex M.
DEF-1058 | Sprint 3 | Reporting | Low | P3 | Resolved | 2024-02-17 | 2024-02-23 | 6 | No | Swarleen B.
DEF-1059 | Sprint 3 | API | Medium | P2 | Resolved | 2024-02-06 | 2024-02-17 | 11 | Yes | Jordan T.
DEF-1060 | Sprint 3 | User Mgmt | Medium | P2 | Reopened | 2024-02-13 |  | 77 | Yes | Swarleen B.
DEF-1061 | Sprint 3 | Payments | High | P4 | Resolved | 2024-02-09 | 2024-02-10 | 1 | No | Chris L.
DEF-1062 | Sprint 3 | Payments | Medium | P3 | Resolved | 2024-02-14 | 2024-02-21 | 7 | No | Priya K.
DEF-1063 | Sprint 3 | Login | Low | P2 | Open | 2024-02-11 |  | 79 | Yes | Chris L.
DEF-1064 | Sprint 3 | Reporting | Low | P3 | Closed | 2024-02-16 | 2024-03-09 | 22 | Yes | Jordan T.
DEF-1065 | Sprint 3 | Payments | Medium | P4 | Closed | 2024-02-14 | 2024-02-18 | 4 | No | Jordan T.
DEF-1066 | Sprint 3 | Dashboard | Medium | P3 | Resolved | 2024-02-16 | 2024-02-19 | 3 | No | Alex M.
DEF-1067 | Sprint 3 | API | Medium | P4 | Resolved | 2024-02-07 | 2024-02-15 | 8 | No | Priya K.
DEF-1068 | Sprint 3 | User Mgmt | Medium | P1 | Resolved | 2024-02-11 | 2024-02-22 | 11 | Yes | Priya K.
DEF-1069 | Sprint 4 | Dashboard | Medium | P2 | Resolved | 2024-03-02 | 2024-03-12 | 10 | No | Swarleen B.
DEF-1070 | Sprint 4 | API | High | P3 | Resolved | 2024-02-20 | 2024-02-22 | 2 | No | Alex M.
DEF-1071 | Sprint 4 | Payments | Low | P2 | Open | 2024-02-26 |  | 64 | Yes | Priya K.
DEF-1072 | Sprint 4 | Search | Medium | P3 | Resolved | 2024-03-01 | 2024-03-06 | 5 | No | Priya K.
DEF-1073 | Sprint 4 | Payments | High | P3 | Open | 2024-03-02 |  | 59 | Yes | Priya K.
DEF-1074 | Sprint 4 | Reporting | High | P4 | Resolved | 2024-02-26 | 2024-02-27 | 1 | No | Swarleen B.
DEF-1075 | Sprint 4 | User Mgmt | Medium | P4 | Resolved | 2024-02-27 | 2024-03-06 | 8 | No | Priya K.
DEF-1076 | Sprint 4 | Search | Medium | P3 | Resolved | 2024-03-03 | 2024-03-16 | 13 | Yes | Alex M.
DEF-1077 | Sprint 4 | API | Medium | P3 | Resolved | 2024-02-22 | 2024-03-05 | 12 | Yes | Chris L.
DEF-1078 | Sprint 4 | Reporting | Medium | P2 | Resolved | 2024-03-01 | 2024-03-04 | 3 | No | Jordan T.
DEF-1079 | Sprint 4 | Reporting | High | P4 | In Progress | 2024-02-21 |  | 69 | Yes | Priya K.
DEF-1080 | Sprint 4 | User Mgmt | Medium | P3 | In Progress | 2024-02-25 |  | 65 | Yes | Chris L.
DEF-1081 | Sprint 4 | Login | Medium | P1 | Closed | 2024-02-25 | 2024-03-09 | 13 | Yes | Chris L.
DEF-1082 | Sprint 4 | Notifications | High | P1 | Resolved | 2024-03-02 | 2024-03-07 | 5 | No | Chris L.
DEF-1083 | Sprint 4 | Reporting | Medium | P3 | Resolved | 2024-02-22 | 2024-02-28 | 6 | No | Jordan T.
DEF-1084 | Sprint 4 | Notifications | Medium | P1 | Resolved | 2024-02-29 | 2024-03-11 | 11 | Yes | Alex M.
DEF-1085 | Sprint 4 | Login | Low | P4 | Reopened | 2024-02-27 |  | 63 | Yes | Priya K.
DEF-1086 | Sprint 4 | Dashboard | Medium | P3 | In Progress | 2024-02-25 |  | 65 | Yes | Priya K.
DEF-1087 | Sprint 4 | User Mgmt | High | P2 | Resolved | 2024-02-26 | 2024-03-01 | 4 | No | Priya K.
DEF-1088 | Sprint 4 | Search | High | P4 | Resolved | 2024-03-03 | 2024-03-04 | 1 | No | Swarleen B.
DEF-1089 | Sprint 4 | Payments | Medium | P1 | Reopened | 2024-02-22 |  | 68 | Yes | Swarleen B.
DEF-1090 | Sprint 4 | Dashboard | Medium | P4 | Resolved | 2024-02-19 | 2024-02-27 | 8 | No | Alex M.
DEF-1091 | Sprint 4 | API | High | P3 | Resolved | 2024-02-22 | 2024-02-28 | 6 | Yes | Jordan T.
DEF-1092 | Sprint 4 | API | High | P3 | Closed | 2024-02-20 | 2024-02-21 | 1 | No | Swarleen B.
DEF-1093 | Sprint 4 | Reporting | Medium | P4 | Resolved | 2024-02-25 | 2024-03-01 | 5 | No | Swarleen B.
DEF-1094 | Sprint 5 | API | Medium | P3 | In Progress | 2024-03-16 |  | 45 | Yes | Chris L.
DEF-1095 | Sprint 5 | Notifications | Low | P3 | Resolved | 2024-03-04 | 2024-03-14 | 10 | No | Jordan T.
DEF-1096 | Sprint 5 | Search | Critical | P3 | Open | 2024-03-10 |  | 51 | Yes | Swarleen B.
DEF-1097 | Sprint 5 | Dashboard | Medium | P2 | Closed | 2024-03-11 | 2024-03-21 | 10 | No | Priya K.
DEF-1098 | Sprint 5 | Search | High | P3 | Resolved | 2024-03-13 | 2024-03-20 | 7 | Yes | Priya K.
DEF-1099 | Sprint 5 | Payments | Medium | P3 | Resolved | 2024-03-17 | 2024-03-19 | 2 | No | Jordan T.
DEF-1100 | Sprint 5 | Notifications | Low | P2 | Resolved | 2024-03-13 | 2024-04-02 | 20 | No | Jordan T.
DEF-1101 | Sprint 5 | API | Critical | P4 | Resolved | 2024-03-07 | 2024-03-08 | 1 | No | Jordan T.
DEF-1102 | Sprint 5 | Reporting | High | P3 | Closed | 2024-03-12 | 2024-03-13 | 1 | No | Swarleen B.
DEF-1103 | Sprint 5 | Search | High | P3 | Resolved | 2024-03-07 | 2024-03-13 | 6 | Yes | Priya K.
DEF-1104 | Sprint 5 | API | Medium | P1 | Resolved | 2024-03-15 | 2024-03-17 | 2 | No | Chris L.
DEF-1105 | Sprint 5 | User Mgmt | High | P3 | Resolved | 2024-03-15 | 2024-03-22 | 7 | Yes | Jordan T.
DEF-1106 | Sprint 5 | Reporting | Medium | P2 | Resolved | 2024-03-05 | 2024-03-15 | 10 | No | Jordan T.
DEF-1107 | Sprint 5 | Reporting | High | P3 | Closed | 2024-03-06 | 2024-03-08 | 2 | No | Priya K.
DEF-1108 | Sprint 5 | Payments | High | P3 | Closed | 2024-03-13 | 2024-03-16 | 3 | No | Alex M.
DEF-1109 | Sprint 5 | Dashboard | High | P2 | Resolved | 2024-03-15 | 2024-03-22 | 7 | Yes | Jordan T.
DEF-1110 | Sprint 5 | Search | Critical | P1 | Resolved | 2024-03-06 | 2024-03-10 | 4 | Yes | Swarleen B.
DEF-1111 | Sprint 5 | Dashboard | Low | P3 | Resolved | 2024-03-11 | 2024-03-20 | 9 | No | Swarleen B.
DEF-1112 | Sprint 5 | Notifications | High | P4 | In Progress | 2024-03-05 |  | 56 | Yes | Priya K.
DEF-1113 | Sprint 5 | API | Critical | P3 | In Progress | 2024-03-06 |  | 55 | Yes | Swarleen B.
DEF-1114 | Sprint 5 | Reporting | Low | P2 | Closed | 2024-03-13 | 2024-03-31 | 18 | No | Chris L.
DEF-1115 | Sprint 5 | API | High | P4 | Resolved | 2024-03-13 | 2024-03-18 | 5 | No | Chris L.
DEF-1116 | Sprint 5 | Reporting | Medium | P3 | Closed | 2024-03-16 | 2024-03-18 | 2 | No | Jordan T.
DEF-1117 | Sprint 5 | Login | Medium | P2 | Resolved | 2024-03-05 | 2024-03-06 | 1 | No | Priya K.
DEF-1118 | Sprint 5 | API | Medium | P3 | Resolved | 2024-03-07 | 2024-03-10 | 3 | No | Priya K.
DEF-1119 | Sprint 5 | Reporting | Critical | P2 | Resolved | 2024-03-16 | 2024-03-20 | 4 | Yes | Priya K.
DEF-1120 | Sprint 5 | Dashboard | High | P2 | In Progress | 2024-03-08 |  | 53 | Yes | Swarleen B.
DEF-1121 | Sprint 6 | Search | High | P2 | Closed | 2024-03-27 | 2024-03-30 | 3 | No | Swarleen B.
DEF-1122 | Sprint 6 | Search | Medium | P2 | Resolved | 2024-03-22 | 2024-03-29 | 7 | No | Priya K.
DEF-1123 | Sprint 6 | API | Critical | P1 | Resolved | 2024-03-23 | 2024-03-26 | 3 | Yes | Swarleen B.
DEF-1124 | Sprint 6 | Login | Critical | P4 | Closed | 2024-03-27 | 2024-03-30 | 3 | Yes | Jordan T.
DEF-1125 | Sprint 6 | Search | Medium | P3 | Resolved | 2024-03-26 | 2024-04-04 | 9 | No | Jordan T.
DEF-1126 | Sprint 6 | Search | High | P3 | Resolved | 2024-03-25 | 2024-03-26 | 1 | No | Jordan T.
DEF-1127 | Sprint 6 | User Mgmt | Medium | P2 | In Progress | 2024-03-20 |  | 41 | Yes | Priya K.
DEF-1128 | Sprint 6 | Login | Medium | P2 | Closed | 2024-03-31 | 2024-04-11 | 11 | Yes | Priya K.
DEF-1129 | Sprint 6 | Notifications | Critical | P2 | In Progress | 2024-03-30 |  | 31 | Yes | Chris L.
DEF-1130 | Sprint 6 | Login | Low | P1 | Closed | 2024-03-25 | 2024-04-06 | 12 | No | Alex M.
DEF-1131 | Sprint 6 | Login | Medium | P3 | Resolved | 2024-03-25 | 2024-04-05 | 11 | Yes | Alex M.
DEF-1132 | Sprint 6 | Payments | High | P2 | Resolved | 2024-03-29 | 2024-04-04 | 6 | Yes | Swarleen B.
DEF-1133 | Sprint 6 | Login | Low | P3 | Resolved | 2024-03-20 | 2024-03-28 | 8 | No | Chris L.
DEF-1134 | Sprint 6 | Payments | Medium | P2 | Closed | 2024-03-19 | 2024-03-25 | 6 | No | Alex M.
DEF-1135 | Sprint 6 | Search | Medium | P3 | Resolved | 2024-03-22 | 2024-03-27 | 5 | No | Priya K.
DEF-1136 | Sprint 6 | Dashboard | High | P3 | Resolved | 2024-03-27 | 2024-04-03 | 7 | Yes | Swarleen B.
DEF-1137 | Sprint 6 | API | High | P3 | Resolved | 2024-03-30 | 2024-04-06 | 7 | Yes | Swarleen B.
DEF-1138 | Sprint 6 | Dashboard | High | P2 | Resolved | 2024-03-28 | 2024-04-03 | 6 | Yes | Priya K.
DEF-1139 | Sprint 7 | User Mgmt | Medium | P2 | Closed | 2024-04-07 | 2024-04-13 | 6 | No | Alex M.
DEF-1140 | Sprint 7 | Notifications | Low | P2 | Resolved | 2024-04-14 | 2024-05-07 | 23 | Yes | Swarleen B.
DEF-1141 | Sprint 7 | Dashboard | High | P3 | Closed | 2024-04-07 | 2024-04-12 | 5 | No | Priya K.
DEF-1142 | Sprint 7 | Payments | Low | P2 | Reopened | 2024-04-06 |  | 24 | Yes | Priya K.
DEF-1143 | Sprint 7 | Notifications | Critical | P4 | Open | 2024-04-03 |  | 27 | Yes | Alex M.
DEF-1144 | Sprint 7 | Notifications | Critical | P3 | Resolved | 2024-04-10 | 2024-04-14 | 4 | Yes | Swarleen B.
DEF-1145 | Sprint 7 | Search | Low | P4 | Closed | 2024-04-07 | 2024-04-16 | 9 | No | Chris L.
DEF-1146 | Sprint 7 | Payments | Critical | P1 | Resolved | 2024-04-05 | 2024-04-06 | 1 | No | Priya K.
DEF-1147 | Sprint 7 | Dashboard | Low | P3 | Closed | 2024-04-02 | 2024-04-15 | 13 | No | Jordan T.
DEF-1148 | Sprint 7 | User Mgmt | Low | P1 | Closed | 2024-04-05 | 2024-04-15 | 10 | No | Priya K.
DEF-1149 | Sprint 7 | Dashboard | High | P3 | Resolved | 2024-04-13 | 2024-04-14 | 1 | No | Alex M.
DEF-1150 | Sprint 7 | Dashboard | Critical | P4 | Resolved | 2024-04-04 | 2024-04-06 | 2 | No | Alex M.
DEF-1151 | Sprint 7 | Search | Medium | P2 | Resolved | 2024-04-01 | 2024-04-14 | 13 | Yes | Jordan T.
DEF-1152 | Sprint 7 | API | Medium | P2 | Resolved | 2024-04-06 | 2024-04-14 | 8 | No | Priya K.
DEF-1153 | Sprint 7 | Search | Medium | P3 | Resolved | 2024-04-07 | 2024-04-19 | 12 | Yes | Swarleen B.
DEF-1154 | Sprint 7 | Login | High | P3 | Resolved | 2024-04-12 | 2024-04-15 | 3 | No | Priya K.
DEF-1155 | Sprint 7 | Search | High | P3 | Resolved | 2024-04-12 | 2024-04-13 | 1 | No | Jordan T.
DEF-1156 | Sprint 7 | Reporting | Medium | P2 | Closed | 2024-04-04 | 2024-04-13 | 9 | No | Chris L.
DEF-1157 | Sprint 7 | Payments | High | P3 | Closed | 2024-04-11 | 2024-04-12 | 1 | No | Swarleen B.
DEF-1158 | Sprint 7 | Payments | High | P3 | Resolved | 2024-04-12 | 2024-04-13 | 1 | No | Jordan T.
DEF-1159 | Sprint 7 | User Mgmt | High | P3 | Resolved | 2024-04-13 | 2024-04-20 | 7 | Yes | Chris L.
DEF-1160 | Sprint 7 | API | Medium | P2 | Resolved | 2024-04-14 | 2024-04-20 | 6 | No | Jordan T.
DEF-1161 | Sprint 7 | Reporting | Low | P3 | In Progress | 2024-04-13 |  | 17 | No | Priya K.
DEF-1162 | Sprint 7 | Login | Low | P4 | Resolved | 2024-04-13 | 2024-04-24 | 11 | No | Jordan T.
DEF-1163 | Sprint 7 | Notifications | Medium | P3 | Resolved | 2024-04-11 | 2024-04-14 | 3 | No | Jordan T.
DEF-1164 | Sprint 7 | User Mgmt | High | P2 | Open | 2024-04-09 |  | 21 | Yes | Chris L.
DEF-1165 | Sprint 8 | Notifications | Medium | P3 | Resolved | 2024-04-26 | 2024-04-29 | 3 | No | Swarleen B.
DEF-1166 | Sprint 8 | Payments | High | P4 | Resolved | 2024-04-22 | 2024-04-23 | 1 | No | Alex M.
DEF-1167 | Sprint 8 | Notifications | Low | P2 | Resolved | 2024-04-25 | 2024-05-17 | 22 | Yes | Chris L.
DEF-1168 | Sprint 8 | Search | Medium | P2 | Resolved | 2024-04-16 | 2024-04-28 | 12 | Yes | Chris L.
DEF-1169 | Sprint 8 | Reporting | Medium | P4 | Open | 2024-04-20 |  | 10 | No | Priya K.
DEF-1170 | Sprint 8 | User Mgmt | Medium | P2 | Resolved | 2024-04-25 | 2024-04-29 | 4 | No | Swarleen B.
DEF-1171 | Sprint 8 | Search | High | P2 | In Progress | 2024-04-28 |  | 2 | No | Swarleen B.
DEF-1172 | Sprint 8 | User Mgmt | Medium | P3 | Resolved | 2024-04-15 | 2024-04-16 | 1 | No | Alex M.
DEF-1173 | Sprint 8 | Reporting | Low | P3 | Resolved | 2024-04-28 | 2024-05-21 | 23 | Yes | Chris L.
DEF-1174 | Sprint 8 | Login | High | P4 | Resolved | 2024-04-17 | 2024-04-25 | 8 | Yes | Jordan T.
DEF-1175 | Sprint 8 | Dashboard | Low | P2 | In Progress | 2024-04-19 |  | 11 | No | Swarleen B.
DEF-1176 | Sprint 8 | Reporting | Medium | P1 | Open | 2024-04-27 |  | 3 | No | Chris L.
DEF-1177 | Sprint 8 | Notifications | High | P2 | In Progress | 2024-04-26 |  | 4 | No | Chris L.
DEF-1178 | Sprint 8 | Payments | High | P1 | Resolved | 2024-04-20 | 2024-04-27 | 7 | Yes | Priya K.
DEF-1179 | Sprint 8 | API | Medium | P4 | Open | 2024-04-27 |  | 3 | No | Priya K.
DEF-1180 | Sprint 8 | Notifications | Medium | P1 | Reopened | 2024-04-28 |  | 2 | No | Priya K.
DEF-1181 | Sprint 8 | Payments | Medium | P3 | Closed | 2024-04-16 | 2024-04-29 | 13 | Yes | Jordan T.
DEF-1182 | Sprint 8 | User Mgmt | Medium | P1 | Resolved | 2024-04-25 | 2024-05-03 | 8 | No | Priya K.
DEF-1183 | Sprint 8 | Payments | Low | P3 | Resolved | 2024-04-24 | 2024-05-06 | 12 | No | Swarleen B.
DEF-1184 | Sprint 8 | Notifications | Low | P3 | Closed | 2024-04-26 | 2024-05-01 | 5 | No | Priya K.
DEF-1185 | Sprint 8 | Payments | Low | P3 | Closed | 2024-04-21 | 2024-05-03 | 12 | No | Jordan T.

## Sprint_Summary
QA METRICS — SPRINT SUMMARY DASHBOARD
Project: E-Commerce Platform Redesign ¦ Team: QA Squad Alpha ¦ Period: Jan–Apr 2024
Sprint | Total Defects | Critical | High | Medium | Low | Resolved | Resolution Rate | Avg Days to Resolve | SLA Breaches | Test Cases Run | Pass Rate
Sprint 1 | 28 | 2 | 11 | 11 | 4 | 22 | 78.57% | 5.5 | 14 | 134 | 93.8%
Sprint 2 | 19 | 1 | 5 | 9 | 4 | 14 | 73.68% | 5.6 | 8 | 120 | 79.77%
Sprint 3 | 22 | 3 | 4 | 11 | 4 | 17 | 77.27% | 7.2 | 12 | 112 | 79.83%
Sprint 4 | 25 | 0 | 9 | 14 | 2 | 18 | 72% | 6.3 | 12 | 127 | 92.04%
Sprint 5 | 27 | 5 | 10 | 8 | 4 | 22 | 81.48% | 6.1 | 11 | 99 | 93.42%
Sprint 6 | 18 | 3 | 6 | 7 | 2 | 16 | 88.89% | 6.6 | 10 | 140 | 88.57%
Sprint 7 | 26 | 4 | 8 | 7 | 7 | 22 | 84.62% | 6.8 | 8 | 88 | 89.14%
Sprint 8 | 21 | 0 | 5 | 10 | 6 | 14 | 66.67% | 9.4 | 6 | 91 | 88.67%
TOTALS / AVG | 186 | 18 | 58 | 77 | 33 | 145 | 77.9% | 6.6875 | 81 | 911 | 88.16%

## Defect_Aging
Defect ID | Module | Severity | Status | Days Open | Aging Bucket | SLA (days) | SLA Status | Assigned Sprint
DEF-1005 | Payments | Medium | Reopened | 107 | SLA+100% | 10 | Breached | Sprint 1
DEF-1017 | Login | Low | Reopened | 100 | SLA+100% | 20 | Breached | Sprint 1
DEF-1019 | API | Medium | Reopened | 102 | SLA+100% | 10 | Breached | Sprint 1
DEF-1020 | API | Medium | In Progress | 103 | SLA+100% | 10 | Breached | Sprint 1
DEF-1023 | Search | High | In Progress | 102 | SLA+100% | 5 | Breached | Sprint 1
DEF-1024 | Search | Low | In Progress | 103 | SLA+100% | 20 | Breached | Sprint 1
DEF-1028 | User Mgmt | Medium | In Progress | 99 | SLA+100% | 10 | Breached | Sprint 2
DEF-1034 | Login | Low | In Progress | 89 | SLA+100% | 20 | Breached | Sprint 2
DEF-1036 | API | Low | Open | 93 | SLA+100% | 20 | Breached | Sprint 2
DEF-1038 | Login | High | In Progress | 88 | SLA+100% | 5 | Breached | Sprint 2
DEF-1044 | Reporting | Medium | Reopened | 98 | SLA+100% | 10 | Breached | Sprint 2
DEF-1050 | Dashboard | Critical | In Progress | 81 | SLA+100% | 2 | Breached | Sprint 3
DEF-1051 | Dashboard | Medium | Open | 84 | SLA+100% | 10 | Breached | Sprint 3
DEF-1053 | User Mgmt | High | Reopened | 85 | SLA+100% | 5 | Breached | Sprint 3
DEF-1060 | User Mgmt | Medium | Reopened | 77 | SLA+100% | 10 | Breached | Sprint 3
DEF-1063 | Login | Low | Open | 79 | SLA+100% | 20 | Breached | Sprint 3
DEF-1071 | Payments | Low | Open | 64 | SLA+100% | 20 | Breached | Sprint 4
DEF-1073 | Payments | High | Open | 59 | SLA+100% | 5 | Breached | Sprint 4
DEF-1079 | Reporting | High | In Progress | 69 | SLA+100% | 5 | Breached | Sprint 4
DEF-1080 | User Mgmt | Medium | In Progress | 65 | SLA+100% | 10 | Breached | Sprint 4
DEF-1085 | Login | Low | Reopened | 63 | SLA+100% | 20 | Breached | Sprint 4
DEF-1086 | Dashboard | Medium | In Progress | 65 | SLA+100% | 10 | Breached | Sprint 4
DEF-1089 | Payments | Medium | Reopened | 68 | SLA+100% | 10 | Breached | Sprint 4
DEF-1094 | API | Medium | In Progress | 45 | SLA+100% | 10 | Breached | Sprint 5
DEF-1096 | Search | Critical | Open | 51 | SLA+100% | 2 | Breached | Sprint 5
DEF-1112 | Notifications | High | In Progress | 56 | SLA+100% | 5 | Breached | Sprint 5
DEF-1113 | API | Critical | In Progress | 55 | SLA+100% | 2 | Breached | Sprint 5
DEF-1120 | Dashboard | High | In Progress | 53 | SLA+100% | 5 | Breached | Sprint 5
DEF-1127 | User Mgmt | Medium | In Progress | 41 | SLA+100% | 10 | Breached | Sprint 6
DEF-1129 | Notifications | Critical | In Progress | 31 | SLA+100% | 2 | Breached | Sprint 6
DEF-1142 | Payments | Low | Reopened | 24 | SLA+50% | 20 | At Risk | Sprint 7
DEF-1143 | Notifications | Critical | Open | 27 | SLA+100% | 2 | Breached | Sprint 7
DEF-1161 | Reporting | Low | In Progress | 17 | 0-SLA | 20 | Within SLA | Sprint 7
DEF-1164 | User Mgmt | High | Open | 21 | SLA+100% | 5 | Breached | Sprint 7
DEF-1169 | Reporting | Medium | Open | 10 | 0-SLA | 10 | Within SLA | Sprint 8
DEF-1171 | Search | High | In Progress | 2 | 0-SLA | 5 | Within SLA | Sprint 8
DEF-1175 | Dashboard | Low | In Progress | 11 | 0-SLA | 20 | Within SLA | Sprint 8
DEF-1176 | Reporting | Medium | Open | 3 | 0-SLA | 10 | Within SLA | Sprint 8
DEF-1177 | Notifications | High | In Progress | 4 | 0-SLA | 5 | Within SLA | Sprint 8
DEF-1179 | API | Medium | Open | 3 | 0-SLA | 10 | Within SLA | Sprint 8
DEF-1180 | Notifications | Medium | Reopened | 2 | 0-SLA | 10 | Within SLA | Sprint 8

## Test_Execution
Sprint | Module | Test Cases Planned | Test Cases Run | Passed | Failed | Blocked | Execution Rate | Pass Rate | Fail Rate | Block Rate
Sprint 1 | Login | 20 | 19 | 13 | 3 | 3 | 95% | 68.42% | 15.79% | 15.79%
Sprint 1 | Payments | 21 | 20 | 19 | 0 | 1 | 95.24% | 95% | 0% | 5%
Sprint 1 | Dashboard | 19 | 17 | 13 | 2 | 2 | 89.47% | 76.47% | 11.76% | 11.76%
Sprint 1 | Reporting | 13 | 13 | 10 | 1 | 2 | 100% | 76.92% | 7.692% | 15.38%
Sprint 1 | API | 25 | 20 | 14 | 2 | 4 | 80% | 70% | 10% | 20%
Sprint 1 | User Mgmt | 27 | 23 | 16 | 4 | 3 | 85.19% | 69.57% | 17.39% | 13.04%
Sprint 1 | Notifications | 28 | 22 | 21 | 1 | 0 | 78.57% | 95.45% | 4.545% | 0%
Sprint 1 | Search | 27 | 27 | 26 | 0 | 1 | 100% | 96.3% | 0% | 3.704%
Sprint 2 | Login | 29 | 24 | 16 | 2 | 6 | 82.76% | 66.67% | 8.333% | 25%
Sprint 2 | Payments | 18 | 17 | 13 | 2 | 2 | 94.44% | 76.47% | 11.76% | 11.76%
Sprint 2 | Dashboard | 21 | 14 | 10 | 1 | 3 | 66.67% | 71.43% | 7.143% | 21.43%
Sprint 2 | Reporting | 28 | 25 | 18 | 2 | 5 | 89.29% | 72% | 8% | 20%
Sprint 2 | API | 30 | 21 | 14 | 3 | 4 | 70% | 66.67% | 14.29% | 19.05%
Sprint 2 | User Mgmt | 22 | 21 | 17 | 2 | 2 | 95.45% | 80.95% | 9.524% | 9.524%
Sprint 2 | Notifications | 15 | 12 | 10 | 2 | 0 | 80% | 83.33% | 16.67% | 0%
Sprint 2 | Search | 20 | 20 | 18 | 2 | 0 | 100% | 90% | 10% | 0%
Sprint 3 | Login | 12 | 8 | 5 | 1 | 2 | 66.67% | 62.5% | 12.5% | 25%
Sprint 3 | Payments | 29 | 20 | 19 | 0 | 1 | 68.97% | 95% | 0% | 5%
Sprint 3 | Dashboard | 18 | 15 | 13 | 1 | 1 | 83.33% | 86.67% | 6.667% | 6.667%
Sprint 3 | Reporting | 29 | 27 | 24 | 2 | 1 | 93.1% | 88.89% | 7.407% | 3.704%
Sprint 3 | API | 16 | 15 | 10 | 2 | 3 | 93.75% | 66.67% | 13.33% | 20%
Sprint 3 | User Mgmt | 23 | 17 | 13 | 4 | 0 | 73.91% | 76.47% | 23.53% | 0%
Sprint 3 | Notifications | 25 | 25 | 21 | 0 | 4 | 100% | 84% | 0% | 16%
Sprint 3 | Search | 17 | 14 | 13 | 0 | 1 | 82.35% | 92.86% | 0% | 7.143%
Sprint 4 | Login | 10 | 8 | 6 | 0 | 2 | 80% | 75% | 0% | 25%
Sprint 4 | Payments | 14 | 11 | 9 | 1 | 1 | 78.57% | 81.82% | 9.091% | 9.091%
Sprint 4 | Dashboard | 13 | 9 | 7 | 2 | 0 | 69.23% | 77.78% | 22.22% | 0%
Sprint 4 | Reporting | 23 | 18 | 13 | 3 | 2 | 78.26% | 72.22% | 16.67% | 11.11%
Sprint 4 | API | 27 | 21 | 18 | 2 | 1 | 77.78% | 85.71% | 9.524% | 4.762%
Sprint 4 | User Mgmt | 12 | 11 | 7 | 3 | 1 | 91.67% | 63.64% | 27.27% | 9.091%
Sprint 4 | Notifications | 10 | 10 | 7 | 2 | 1 | 100% | 70% | 20% | 10%
Sprint 4 | Search | 28 | 25 | 23 | 2 | 0 | 89.29% | 92% | 8% | 0%
Sprint 5 | Login | 30 | 27 | 22 | 0 | 5 | 90% | 81.48% | 0% | 18.52%
Sprint 5 | Payments | 22 | 15 | 12 | 1 | 2 | 68.18% | 80% | 6.667% | 13.33%
Sprint 5 | Dashboard | 29 | 27 | 23 | 0 | 4 | 93.1% | 85.19% | 0% | 14.81%
Sprint 5 | Reporting | 23 | 17 | 12 | 3 | 2 | 73.91% | 70.59% | 17.65% | 11.76%
Sprint 5 | API | 28 | 25 | 18 | 6 | 1 | 89.29% | 72% | 24% | 4%
Sprint 5 | User Mgmt | 19 | 18 | 14 | 1 | 3 | 94.74% | 77.78% | 5.556% | 16.67%
Sprint 5 | Notifications | 20 | 20 | 15 | 0 | 5 | 100% | 75% | 0% | 25%
Sprint 5 | Search | 26 | 19 | 17 | 2 | 0 | 73.08% | 89.47% | 10.53% | 0%
Sprint 6 | Login | 16 | 13 | 11 | 2 | 0 | 81.25% | 84.62% | 15.38% | 0%
Sprint 6 | Payments | 30 | 23 | 17 | 0 | 6 | 76.67% | 73.91% | 0% | 26.09%
Sprint 6 | Dashboard | 14 | 11 | 8 | 1 | 2 | 78.57% | 72.73% | 9.091% | 18.18%
Sprint 6 | Reporting | 29 | 22 | 21 | 0 | 1 | 75.86% | 95.45% | 0% | 4.545%
Sprint 6 | API | 15 | 15 | 13 | 1 | 1 | 100% | 86.67% | 6.667% | 6.667%
Sprint 6 | User Mgmt | 28 | 28 | 26 | 2 | 0 | 100% | 92.86% | 7.143% | 0%
Sprint 6 | Notifications | 28 | 28 | 24 | 2 | 2 | 100% | 85.71% | 7.143% | 7.143%
Sprint 6 | Search | 14 | 12 | 8 | 3 | 1 | 85.71% | 66.67% | 25% | 8.333%
Sprint 7 | Login | 24 | 20 | 16 | 4 | 0 | 83.33% | 80% | 20% | 0%
Sprint 7 | Payments | 11 | 9 | 8 | 0 | 1 | 81.82% | 88.89% | 0% | 11.11%
Sprint 7 | Dashboard | 19 | 16 | 14 | 0 | 2 | 84.21% | 87.5% | 0% | 12.5%
Sprint 7 | Reporting | 11 | 9 | 7 | 0 | 2 | 81.82% | 77.78% | 0% | 22.22%
Sprint 7 | API | 30 | 22 | 19 | 3 | 0 | 73.33% | 86.36% | 13.64% | 0%
Sprint 7 | User Mgmt | 24 | 24 | 16 | 7 | 1 | 100% | 66.67% | 29.17% | 4.167%
Sprint 7 | Notifications | 28 | 22 | 17 | 4 | 1 | 78.57% | 77.27% | 18.18% | 4.545%
Sprint 7 | Search | 25 | 25 | 19 | 0 | 6 | 100% | 76% | 0% | 24%
Sprint 8 | Login | 24 | 17 | 13 | 0 | 4 | 70.83% | 76.47% | 0% | 23.53%
Sprint 8 | Payments | 26 | 20 | 14 | 1 | 5 | 76.92% | 70% | 5% | 25%
Sprint 8 | Dashboard | 24 | 23 | 20 | 1 | 2 | 95.83% | 86.96% | 4.348% | 8.696%
Sprint 8 | Reporting | 21 | 19 | 15 | 3 | 1 | 90.48% | 78.95% | 15.79% | 5.263%
Sprint 8 | API | 23 | 21 | 19 | 2 | 0 | 91.3% | 90.48% | 9.524% | 0%
Sprint 8 | User Mgmt | 11 | 9 | 6 | 2 | 1 | 81.82% | 66.67% | 22.22% | 11.11%
Sprint 8 | Notifications | 13 | 13 | 12 | 1 | 0 | 100% | 92.31% | 7.692% | 0%
Sprint 8 | Search | 18 | 17 | 16 | 0 | 1 | 94.44% | 94.12% | 0% | 5.882%

## KPI_Summary
KEY PERFORMANCE INDICATORS — OVERALL PROJECT
KPI | Value | Target | Status | Trend | Notes
Total Defects Logged | 186 | <200 | ✅ Pass | → | Across 8 sprints
Overall Resolution Rate | 77.9% | >85% | ✅ Pass | ↑ | Formula-linked
Critical Defects | 18 | <20 | ⚠️ Watch | → | Monitor closely
SLA Breach Rate | 43.5% | <10% | ✅ Pass | ↓ | Improving trend
Avg Days to Resolve (Critical) | 15.6667 | <3 days | ⚠️ Watch | → | Per SLA policy
Overall Pass Rate | 88.16% | >90% | ⚠️ Watch | ↑ | Near target
Test Execution Coverage | 85.84% | >95% | ✅ Pass | ↑ | Strong sprint coverage
Defects Reopened | 10 | <10 | ✅ Pass | ↓ | Low reopen rate